ROTARY IT FELLOWSHIP · THE QUANTUM ACCELERATOR

Community assessment toolkit

Instruments, sampling plan and results form for the assessment every humanitarian global grant requires.

Why this one matters more than the rest The Rotary Foundation publishes four reasons global grant applications are most often denied. One of them is, in its own words, “a community assessment was not conducted.” Activities must respond to the findings of an assessment and be designed in collaboration with the host community. Two practical constraints catch people out. First, at least two stakeholder groups fairly representing the community must be consulted — two groups who already agree with each other do not count. Second, a global grant cannot pay for the assessment. Fund it with a district grant or club funds.

# 1 · Plan the assessment

## Choose your methods

Use at least two. A site visit on its own is not an assessment — reviewers look for a method with a name, a sample and a date.

| Method | Best for | Typical effort | Used? (date) |
| --- | --- | --- | --- |
| Household survey | Counting things: distances, times, costs, coverage, practice rates. Gives you the baseline numbers your measurement plan will need. | 2–4 weeks |  |
| Focus group discussion | Understanding why something is the way it is, and surfacing disagreement between groups. | 1–2 days each |  |
| Key informant interview | Officials, clinicians, head teachers, water engineers — people who hold information nobody else has. | 1 hour each |  |
| Community meeting | Testing a proposed design in public and recording objections. | Half a day |  |
| Community asset inventory | What already exists and what condition it is in. Often reveals that the real problem is maintenance, not absence. | 2–5 days |  |
| Resource or facility mapping | Where things are relative to the people who need them. | 2–3 days |  |
| Direct observation | Actual practice as opposed to reported practice — essential for behaviour-change measures. | Ongoing |  |
| Review of public records | Clinic registers, school rolls, water point functionality databases. | 1–2 days |  |

Tick the methods you used and record the date. The Foundation's results form asks for both.

## Sampling plan

Name the groups before you start, not afterwards. “The community” is not a stakeholder group; “women who collect water” is.

| Stakeholder group | How many consulted | Method used | Why this group matters here |
| --- | --- | --- | --- |

Minimum two groups, fairly representing the community. Include at least one group that stands to lose something if the project goes ahead — their objection is the most useful information you will collect.

# 2 · Instruments

## Household survey — core questions

Adapt the wording; keep the structure. Every question below exists to produce a number you can measure again at the end.

- Household composition: number of adults, number of children under five, number of people with a disability.

- Current situation: what the household does today about the problem this project addresses.

- Distance and time: how far, how long, how often, and who in the household does it.

- Cost: what the household currently pays, in money or in time, for the alternative.

- Practice: what people actually do, asked in a way that does not signal the desired answer.

- Prior interventions: has anything been provided here before? Is it still working? If not, when and why did it fail?

- Willingness to contribute: would the household pay a tariff, contribute labour, or serve on a committee?

- Who decides: who in the household or community would need to agree for this to work?

The single most persuasive question on this list is the one about prior interventions. An application that says “two handpumps were donated here in 2019 and both failed within eighteen months because there was no maintenance fund and no trained mechanic within 300km, so this project establishes both” is answering the sustainability question before the reviewer asks it.

## Focus group discussion guide

- Opening: what works well here already? (Start with assets, not deficits.)

- The problem in their words: describe a normal day dealing with it.

- Who is most affected, and who is least? Why the difference?

- What has been tried? What happened?

- If money appeared tomorrow, what would this group spend it on — and what would other groups say to that?

- What would have to be true for a solution to still be working in five years?

- Who should own it? Who should maintain it? Who should pay?

- Closing: what have we not asked about that we should have?

Run separate groups where a mixed group would silence someone. Record disagreement rather than resolving it — the disagreement is the finding.

## Key informant interview guide

- What is your role, and what part of this problem do you see that others do not?

- What data do you hold? Can we have it, and how current is it?

- What has been tried here, by whom, and what became of it?

- What would you need in place to support this after the grant closes?

- Is there a government plan, budget line or standard we should align with?

- What is the most likely way this fails?

## Community asset inventory

| Asset or facility | Condition | Who owns it | Who maintains it | Funded how |
| --- | --- | --- | --- | --- |

Assess more than infrastructure. Skills, committees, budgets and relationships are assets too, and their absence is usually the real constraint.

# 3 · Results form

Transfer your findings here. This mirrors the information the Foundation's community assessment results form asks for.

Project title

Community, city or district assessed

Country

Dates the assessment was carried out

Total number of people consulted

Who paid for the assessment (it may not be the global grant)

### Methods used and by whom

### What the assessment found

State findings as findings: what people said, what you counted, what already failed here and why. Numbers where you have them.

# 4 · Findings to design

Write this sentence literally, once per finding: “The assessment found X, therefore the project does Y.” Most applications never state the link, and a reviewer who cannot trace a design decision back to a finding will read the project as a list of things the organisation wanted.

| The assessment found… | …therefore the project does | Which measure will show this worked |
| --- | --- | --- |

# 5 · Traps worth knowing

- Assuming rather than asking. The classic: noticing children sitting on the floor and concluding they need desks, when the head teacher would have told you the roof leaks and attendance collapses in the rainy season.

- One stakeholder group, consulted twice. Two groups who already agree do not satisfy the requirement.

- Assessing infrastructure only. The Foundation expects more than a list of missing objects.

- Charging the assessment to the global grant. It is not an eligible cost. Use a district grant.

- Collecting the baseline after activities have started. The baseline must precede the intervention or it measures nothing.

- An assessment conducted by the international sponsor on a visit. The host sponsor conducts it; that is their defined role.

- Treating a recurring annual service trip as a project. If the same need returns every year, the assessment has not found the cause.

Prepared from the Terms and Conditions for Rotary Foundation Global Grants (July 2026), verified against the source document, together with the Areas of Focus Policy Statements, Community Assessment Tools (605-EN) and the Global Grant Monitoring and Evaluation Plan Supplement. The Foundation may modify its terms at any time; check My Rotary for anything published after July 2026.

Rotary Fellowships are, in Rotary's own words, “global groups that bring people together around shared passions.” The Rotary IT Fellowship is one of more than a hundred listed by Rotary International, governed by the Rotary Fellowships Code of Policies and fiscally sponsored by The Action Group (TAG) Foundation Inc., a 501(c)(3). This template is our own initiative and our own reading of the published rules. It is not operated, endorsed, approved or sponsored by Rotary International or The Rotary Foundation, is not a Rotary Foundation document, is not legal advice, and is not a determination or guarantee of funding. Only The Rotary Foundation approves grants. info@rofit.org